## OBS Maintenance Tracker
| Overall Summary | Count |  | Carrier Maintenance
| New Maintenance | 0 |  | Backbone Maintenance
| Already Notified | 0
| Completed | 0
| Rescheduled | 0
| Cancelled | 0
| Emergency | 0
Date of Report Published | S.No | Haleon Site Id | Impacted CIs | Scope of change | Type of change | City | Country | Region | Scheduled Date (GMT) (Time) | Local Time Zone | Duration of change / impact (MIN) | Maintenance window (in hours) | Service Impact (Yes/ No) | Service Impact in mins | Notification Sent to relevant Haleon Peer Teams( Site leads , SMOps) | Alarm Suppression in place? | Service Desk aligned for monitoring during MW? | Pre - Check? | Post Check? | Status of activity | Any Incidents due to this activity? If yes, Put INC Haleon SNOW facing | Remarks

## Sheet1 (hidden)
Gurmeet Raw Report
Mayank /Gurmeet runs a script
Reports gets generated ( by using the script )
Basic Impact analysis ( )
By using Power Automate , Regional CSM will receive the Report

## Process
Process
Task | Frequency / Owner | Additional Notes
Maintenance Intimation Frequency | Weekly on Tuesday or next business day if a public holiday
External Email Distribution | NWSMOPS, Local Site Leads
Internal Email Distribution | Haleon CSM Distribution, DCSC
CB-CAB | Twice a week (Tuesday & Friday) for 10 mins during SOD by CSM | Reschedule option: No to Limited (due to global changes involving multiple customers) Attempt for resched - QSC , HQ , GCC
Alarm Suppression | Following OB alarm suppression process | Suppression needed for other vendors (TechM) only in case of isolation, via RITM
Owner of Alarm Suppression Process | Orange CSM, Support Team, Haleon Orange DCSC
Escalation in Case of Outage | 24x7 DCSC team with CC to Orange CSM
Pre-Post Checks Submission | Within 2 business days of activity | To be stored at a common SharePoint directly via DCSC or CSM

## Completed
Date of Report Published | S.No | Haleon Site Id | Impacted CIs | Scope of change | Type of change | City | Country | Region | Scheduled Date (GMT) (Time) | Local Time Zone | Duration of change / impact (MIN) | Maintenance window (in hours) | Service Impact (Yes/ No) | Service Impact in mins | Notification Sent to relevant Haleon Peer Teams( Site leads , SMOps) | Alarm Suppression in place? | Service Desk aligned for monitoring during MW? | Pre - Check? | Post Check? | Status of activity
| 1 | NYN | PZRN065 | Due To Planned Maintenance / Works Your Below Mentioned Service Has To Be Interrupted.We Are Anxious To Keep The Necessary Interruption Time As Short As Possible. | Carrier Maintenace | NYON | SWITZERLAND | EUROPE | 06/JAN/2026 12:00:00 AM | CET [GMT+01:00 DST= GMT+02:00] | 5 | 05:00 | No | Traffic will failover to PZRN066. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
| 2 | HCM | PSGN913 | Lptt Perform Network Upgrading/Expanding | Carrier Maintenace | HO CHI MINH | VIET NAM | APAC | 08/JAN/2026 03:30:00 AM | VE [GMT-04:00] | 60 | 04:50 | No | Traffic will failover to PSGN912. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
| 3 | CAP | PCPT666 | During initial implementation of vIGW in MAD and JNB, a command "local-as loops 3" specified in COG (to allow local AS to appera up to 3 times in the received AS-path) was not accepted - most likely because there were configured 2 sessions (old and new). Now when there is only 1 session, please try to apply it again and see if it will be accepted now. | Backbone Maintenance | CAPE TOWN | SOUTH AFRICA | EMEA | 11/JAN/2026 07:00:00 AM | - | 60 | 01:00 | No | Traffic will failover to PCPT665. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
| 4 | STL | PCPS012 | Change Description : BDAL671, BDAL678 and BDAL655 rehome to BDAL9910 Please configure target interfaces and prepare any needed configuration for the below migrations on January 11th at 3 AM GMT. Refer to plan attached and confirm if everything needs is done from my side prior to the migration. iUSTS - BDAL678 Gi0/0 Source PE: BDAL916 Fa5/2/0 Target PE: BDAL9910 ge-0/1/3 -------------------------------- USID: RALI005310 / RALI005311 CDE PE - BDAL671 xe-0/2/0 Source PE: BDAL916 Te3/0/3 Ta | Backbone Maintenance | ST. LOUIS | UNITED STATES | NAM | 11/JAN/2026 03:00:00 AM | - | 1 | 00:01 | No | Traffic will failover to PCPS013. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
| 5 | CQM | PYCV006 | BYUL9910 Junos Upgrade to 23.4R2-S4.11 and JSU install | Backbone Maintenance | MONTRÉAL | CANADA | NAM | 11/JAN/2026 03:00:00 AM | - | 180 | 03:00 | No | Traffic will failover to PYCV007. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
| 6 | LEV | PSLD027 | Hereby We Inform You That Swan Is Going To Do An Planned Maintenance Work, Which Will Affect Your Service. | Carrier Maintenace | LEVICE | SLOVAKIA | EUROPE | 11/JAN/2026 11:01:00 PM | CET [GMT+01:00 DST= GMT+02:00] | 30 | 04:98 | No | Traffic will failover to PSLD026. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
2026-01-14 | 7 | LEV | PSLD026 | Hereby We Inform You That Swan Is Going To Do An Planned Maintenance Work, Which Will Affect Your Service. | Carrier Maintenace | LEVICE | SLOVAKIA | EUROPE | 18/JAN/2026 11:01:00 PM | CET [GMT+01:00 DST= GMT+02:00] | 30 | 04:98 | No | Traffic will failover to PSLD027. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
2026-01-14 | 8 | STL | PCPS012 | Change Description: BDAL671, BDAL678 and BDAL655 rehome to BDAL9910 Please configure target interfaces and prepare any needed configuration for the below migrations on January 11th at 3 AM GMT. Refer to plan attached and confirm if everything needs is done from my side prior to the migration. iUSTS - BDAL678 Gi0/0 Source PE: BDAL916 Fa5/2/0 Target PE: BDAL9910 ge-0/1/3 -------------------------------- USID: RALI005310 / RALI005311 CDE PE - BDAL671 xe-0/2/0 Source PE: BDAL916 Te3/0/3 Target PE: BDAL9910 xe-0/2/5 -------------------------------- For BDAL655 Ten1/2/1 --- BDAL916 Ten3/0/5 PE IBR - BDAL655 xe-1/2/1 Source PE: BDAL916 Te3/0/5 Target PE: BDAL9910 xe-2/1/0:0 FE details : FLIP 18497757 Additional Comments : Migration planned January 11th at 3 AM GMT | Backbone Maintenance | ST. LOUIS | UNITED STATES | NAM | 18/JAN/2026 10:00:00 AM | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | Re-scheduled
2026-01-14 | 9 | MNH | PMUC2640 | Maintenance By The Local Carrier | Carrier Maintenace | MÜNCHEN | GERMANY | EUROPE | 19/JAN/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 45 | 06:00 | No | Traffic will failover to PZMU060. a short blip for failover might experience | Yes | Yes | Yes | Yes | Yes | Completed
2026-01-20 | 10 | ALC | PMAD6083 | Scheduled Maintenance In Our Subcontractor'S Network | Carrier Maintenace | MADRID | SPAIN | EUROPE | 22/JAN/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 420 | 07:00 | No | Traffic will failover to BVPN - Underlay PMAD6082. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-14 | 11 | DUN | PWAT031 | We Require This Maintenance Window To Logically Rehome Services From Erne Street Datacentre To New Datacentre Fenian Street. Planned Works Date & Time: Start Date/Time: 2026-01-20 22:00:00 End Date/Time: 2026-01-21 08:00:00 Maintenance Window Duration: 10 Hours Time Zone: Ist ( Irish Standard Time ) | Carrier Maintenace | DUNGARVAN | IRELAND | EUROPE | 20/JAN/2026 10:00:00 PM | WET [GMT DST= GMT+01:00 ] | 600 | 10:00 | No | Traffic will failover to PWAT038. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-14 | 12 | WNJ | PJVI028 | 39.1611786 / -77.4595716 And 39.1596318 / -77. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 23/JAN/2026 05:00:00 AM | EST [GMT-5:00] | 60 | 06:00 | No | Traffic will failover to PJVI029. a short blip for failover might experience | Yes | Yes | Yes |  |  | Re-scheduled
2026-01-14 | 13 | PAN | PPTY375 | Description Perform Segment Changes In The Campo Lindbergh Sector, Eliminating Multiple Damaged Junction Boxes To Improve Network Performance. | Carrier Maintenace | PANAMA CITY | PANAMA | LAM | 21/JAN/2026 02:00:00 AM | GMT-05:00 | 120 | 09:00 | No | Traffic will failover to PPTY376. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-14 | 14 | IDP | PSLV005 | Ios Upgrade At Gklhptcvt4Cr710 | Carrier Maintenace | BADDI | INDIA | APAC | 22/JAN/2026 06:30:00 PM | IST [GMT+05:30] | 300 | 06:00 | No | Traffic will failover to PSLV006. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 15 | BOO | PCAI1987 | Transmission Migration | Carrier Maintenace | CAIRO | EGYPT | EMEA | 19/JAN/2026 11:00:00 PM | EST [GMT+02:00 DST= GMT+03:00] | 60 | 05:00 | No | Traffic will failover to PCAI1986. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 16 | TRR | PSZT014 | Firmware Update To Prevent Potential Outages During Off-Peak Hours. | Carrier Maintenace | CUAUTITLÁN IZCALLI | MEXICO | LAM | 20/JAN/2026 06:00:00 AM | [GMT-07:00 DST= GMT-06:00] | 300 | 06:00 | No | Traffic will failover to PSZT015. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 17 | ALC | PMAD6082 | Network : OGN Region : EUR Changes Category : traffic deactivation Changes Type : Link Operations Service Impact : Degraded Change Window : WE Priority : 1 Duration : 1 hours Devices : BBCN301 Impacted services : N/A Change Description : The new virtual Internet Gateway has been successfully configured on BCNTR2 OGN P route Therefore, traffic de-activation on bbcn301 can be done now Topology bbcn301 (Te0/1/0) <-i/h-> BBCN816-Ten1/2/0 bbcn301 (Te0/1/1) <- BCNBCN160 -> BCNTR2-TE0/1/0/34/1 Additional Comments: traffic de-activation on bbcn301 | Backbone Maintenance | MADRID | SPAIN | EUROPE | 24/JAN/2026 08:00:00 PM | - | 1 | 00:01 | No | Traffic will failover to BVPN - Underlay PMAD6083. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-23 | 18 | WNJ | PJVI028 | 39.1611786 / -77.4595716 And 39.1596318 / -77. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 2026-02-26 05:00 | EST [GMT-5:00] | 60 | 06:00 | No | Traffic will failover to PJVI029. a short blip for failover might experience | Yes | Yes | Yes |  |  | Cancelled | it was rescheduled to item 30 Change from 26/FEB/2026 05:00:00 AM to 26/FEB/2026 12:00:00 AM GMT
2026-01-20 | 19 | OKH | PHCC017 | Our Provider Will Be Performing Network Maintenance In Mahopac, Ny, To Address A Network Fault And Reduce The Risk Of Unscheduled Impact. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 28/JAN/2026 05:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 1 | 05:00 | No | Traffic will failover to PHCC016. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 20 | OKH | PHCC017 | Our Provider Will Be Performing Network Maintenance In Mahopac, Ny, To Address A Network Fault And Reduce The Risk Of Unscheduled Impact. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 29/JAN/2026 05:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 1 | 05:00 | No | Traffic will failover to PHCC016. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 21 | IAY | PQZR020 | We Would Like To Make You Aware Of A Maintenance Our Carrier Will Conduct On Their Network That Will Affect Your Service. The Maintenance Will Be Carried Out To Improve The Network'S Stability And Service Quality. As This Maintenance Is Not Being Conducted By Colt, Rescheduling This Work May Not Be Possible. Should The Date And Time For The Maintenance Have Passed Without An Updated Notification Being Communicated For It, Please Consider The Work As Completed. | Carrier Maintenace | APRILIA | ITALY | EUROPE | 29/JAN/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 60 | 05:00 | No | Traffic will failover to BVPN - Underlay PQZR021. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 22 | MAX | PDED019 | Ios Upgrade ¦¦ Hwrupbopt4Cr050 | Carrier Maintenace | HARIDWAR | INDIA | APAC | 28/JAN/2026 06:30:00 PM | IST [GMT+05:30] | 120 | 06:00 | Yes | Site will isoloted due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-01-23 | 23 | BSL | PBTS884 | We Would Like To Inform You About A Planned Work On The Part Of Orange Slovensko On January 30 2026 At 01:00 Am Until January 30 2026 At 06:00 Am .The Time Zone Is Cet. | Carrier Maintenace | BRATISLAVA II | SLOVAKIA | EUROPE | 30/JAN/2026 12:00:00 AM | CET [GMT+01:00 DST= GMT+02:00] | 30 | 05:00 | Yes | Site will isolated due to single router | Yes | Yes | Yes |  |  | Completed
2026-01-20 | 24 | MAX | PDED019 | Rkeupsult4Cr04 | Carrier Maintenace | HARIDWAR | INDIA | APAC | 02/FEB/2026 06:30:00 PM | IST [GMT+05:30] | 60 | 06:00 | Yes | Site will isoloted due to Single point of failure | Yes | Yes | Yes |  |  | Cancelled
2026-01-28 | 25 | MAX | PDED019 | Tp To Ip Migration ¦¦ Upw4P19E05_Hwr_4S_Rke_Ot5 ¦¦ Sqkbcluanmht5Cn122126 , Sqk_Bclup_Nmh_P_C61838 | Carrier Maintenace | HARIDWAR | INDIA | APAC | 04/FEB/2026 05:30:00 PM | IST [GMT+05:30] | 60 | 07:00 | Yes | Site will isoloted due to Single point of failure |  | Yes |  |  |  | Completed
2026-01-23 | 26 | NYN | PZRN066 | Need to upgrade BGVA915 (ASR1K) router to version 17.6.6a from version 17.6.4 as this include the BUG fixes (CSCwd81240) which is required in order to fix for CPU utilization from the Linux kernel is at 100% due to btelnet process for customer JTI customer and another BUG "CSCwb61073" which causes a stuck process within BQS that can cause QoS mis-programming. Note: This upgrade is a join risk by Engineering team, GDO team and TAC. As cisco support is not available due to legacy hardware. | Backbone Maintenance | NYON | SWITZERLAND | EUROPE | 31/JAN/2026 10:00:00 PM | - | 30 | 00:30 | No | Traffic will failover to BVPN - Underlay PZRN065. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-28 | 27 | BKK | PBKK2142 | Jastel Will Perform A Mandatory Service Migration To The New Core Network To Optimize Performance And Stability | Carrier Maintenace | PATHUM WAN | THAILAND | APAC | 28/JAN/2026 05:00:00 PM | THA [GMT+07:00] | 30 | 05:00 | No | Traffic will failover to PBAO005. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-30 | 28 | CUD | PSFZ30020 | To Maintain Network Performance And Stability We Will Be Migrating Circuits To An Optimum Fiber Path. | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 12/FEB/2026 11:00:00 PM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will isoloted due to Single point of failure | [5 empty] | Cancelled
2026-01-30 | 29 | BOO | PCAI1987 | Transmission Migration | Carrier Maintenace | CAIRO | EGYPT | EMEA | 30/JAN/2026 11:00:00 PM | EST [GMT+02:00 DST= GMT+03:00] | 60 | 05:00 | No | Traffic will failover to PCAI1986. a short blip for failover might experience | [5 empty] | Completed
2026-01-30 | 30 | BSL | PBTS884 | We Would Like To Inform You About A Planned Work On The Part Of Orange Slovensko On February 05 2026 At 01:00 Am Until February 05 2026 At 06:00 Am . | Carrier Maintenace | BRATISLAVA II | SLOVAKIA | EUROPE | 05/FEB/2026 12:00:00 AM | CET [GMT+01:00 DST= GMT+02:00] | 30 | 05:00 | Yes | Site will isolated due to single router |  | Yes |  |  |  | Completed
2026-02-02 | 31 | PGG | PPSE022 | The Purpose Of This Activity Is To Execute A Software Upgrade. Please Note That Your Services Detailed Above Will Be Affected Up To One (1) Hour During This Activity. | Carrier Maintenace | GUAYAMA | PUERTO RICO | LAM | 06/FEB/2026 05:00:00 AM | AT [GMT-04:00] | 60 | 02:00 | No | Traffic will failover to BVPN - Underlay PPSE021. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-02 | 32 | STL | PCPS012 | SCOPE: activate flexible queuing for FPC 1 on BDAL9910 =========================================== Network : OGN Region : AMER Changes Category : Chassis Components Changes Type : Card configuration - disruptive Service Impact : Yes Change Window : BD LTP Priority : [1] Duration : 2h Devices : BDAL9910 impacted services : Connections on FPC 1 of BDAL9910 Change Description : Queueing activation on FPC 1 - BDAL9910 FE details : n/a - remote change AdditionalComments : Hello team, please see request below: We need to activate flexible queuing for FPC 1 on BDAL9910 to clear some errors we faced during a recent migration. Please perform change on February 9 at 12GMT. ¿set chassis fpc 1 flexible-queuing-mode¿ This change will cause FPC 1 to reload so please notify all the impacted connections via SWAN advisory. bkumar@bdal9910> show interfaces descriptions ¦ match -1/ ¦ match "up up" ge-1/0/0 up up #under configuration ge-1/0/0.2 up up SIEMENS AG - DALLAS - to PDNE028 - Gi0/0/1.2 - 1000000K ge-1/0/1 up up IGN ETH-GE-Nat,VoGW:BDAL715-GE0/0/0,BW:200M,ID:DALDAL255,TYP:SIPC4-GW,TXT:SIP Carrier NICE - Model-D(West) ge-1/0/1.0 up up IGN ETH-GE-Nat,VoGW:BDAL715-GE0/0/0,BW:200M,ID:DALDAL255,TYP:SIPC4-GW,TXT:SIP Carrier NICE - Model-D(West) xe-1/2/0 up up #under configuration xe-1/2/0.204 up up TELEKOMDEUTSCHLAND :IPXT ASN20936 @81.28.66.56 - IPX LD011691 LD018089-LDA13856 :NSO - PrivPeer xe-1/2/1 up up #under configuration xe-1/2/1.320 up up AIRNITY :IPXT ASN65120 @81.52.138.170 - IPX LD020769 LD020770-LDA14614 :NSO - Custom xe-1/2/2 up up TESTING DALIO1 port_4 from BDAL9910 DALDAL264 - IOMETRIX - Backbone xe-1/2/3 up up DALTR3 from BDAL9910 @XXX.XXX.XXX.XXX - L2 switching trunk FIBXXXXX - Backbone xe-1/2/3.100 up up DALIO1 :OINIS - internal vlan 100 - Backbone | Backbone Maintenance | ST. LOUIS | UNITED STATES | NAM | 09/FEB/2026 12:00:00 AM |  | 120 | 2:00 | No | Traffic will failover to PCPS013. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-01-28 | 33 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For Routine Splicing. Your Circuit(S)May Experience Fluctuating Impact, If Down For More Than 10 Minutes Please Call Out Change Management Call Center. We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 11/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to BVPN - Underlay PJVI029. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-02 | 34 | PLA | PLIM1002 | These Works Aim To Keep Our Networks In Optimal Condition. | Carrier Maintenace | SAN ISIDRO | PERU | LAM | 11/FEB/2026 05:00:00 AM | PET [GMT-05:00] | 90 | 5:00 | Yes | Site will isoloted due to Single point of failure |  | Yes |  |  |  | Completed
2026-02-02 | 35 | STL | PCPS012 | SCOPE: activate flexible queuing for FPC 1 on BDAL9910 =========================================== Network : OGN Region : AMER Changes Category : Chassis Components Changes Type : Card configuration - disruptive Service Impact : Yes Change Window : BD LTP Priority : [1] Duration : 2h Devices : BDAL9910 impacted services : Connections on FPC 1 of BDAL9910 Change Description : Queueing activation on FPC 1 - BDAL9910 FE details : n/a - remote change AdditionalComments : Hello team, please see request below: We need to activate flexible queuing for FPC 1 on BDAL9910 to clear some errors we faced during a recent migration. Please perform change on February 9 at 12GMT. ¿set chassis fpc 1 flexible-queuing-mode¿ This change will cause FPC 1 to reload so please notify all the impacted connections via SWAN advisory. bkumar@bdal9910> show interfaces descriptions ¦ match -1/ ¦ match "up up" ge-1/0/0 up up #under configuration ge-1/0/0.2 up up SIEMENS AG - DALLAS - to PDNE028 - Gi0/0/1.2 - 1000000K ge-1/0/1 up up IGN ETH-GE-Nat,VoGW:BDAL715-GE0/0/0,BW:200M,ID:DALDAL255,TYP:SIPC4-GW,TXT:SIP Carrier NICE - Model-D(West) ge-1/0/1.0 up up IGN ETH-GE-Nat,VoGW:BDAL715-GE0/0/0,BW:200M,ID:DALDAL255,TYP:SIPC4-GW,TXT:SIP Carrier NICE - Model-D(West) xe-1/2/0 up up #under configuration xe-1/2/0.204 up up TELEKOMDEUTSCHLAND :IPXT ASN20936 @81.28.66.56 - IPX LD011691 LD018089-LDA13856 :NSO - PrivPeer xe-1/2/1 up up #under configuration xe-1/2/1.320 up up AIRNITY :IPXT ASN65120 @81.52.138.170 - IPX LD020769 LD020770-LDA14614 :NSO - Custom xe-1/2/2 up up TESTING DALIO1 port_4 from BDAL9910 DALDAL264 - IOMETRIX - Backbone xe-1/2/3 up up DALTR3 from BDAL9910 @XXX.XXX.XXX.XXX - L2 switching trunk FIBXXXXX - Backbone xe-1/2/3.100 up up DALIO1 :OINIS - internal vlan 100 - Backbone | Backbone Maintenance | ST. LOUIS | UNITED STATES | NAM | 09/FEB/2026 12:00:00 AM |  | 120 | 2:00 | No | Traffic will failover to PCPS013. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-09 | 36 | PAN | PPTY376 | Activate Dedicated Equipment For Lu Route Reflector Functionality At The Victoria Plaza Node, In Order To Decouple Core Router Functions. | Carrier Maintenace | PANAMA CITY | PANAMA | LAM | 11/FEB/2026 04:00:00 AM | GMT-05:00 | 0 | 04:00 | No | Traffic will failover to BVPN - Underlay PPTY375. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-01-28 | 37 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For Routine Splicing. Your Circuit(S)May Experience Fluctuating Impact, If Down For More Than 10 Minutes Please Call Out Change Management Call Center. We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 11/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to BVPN - Underlay PJVI029. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-02 | 38 | PLA | PLIM1002 | These Works Aim To Keep Our Networks In Optimal Condition. | Carrier Maintenace | SAN ISIDRO | PERU | LAM | 11/FEB/2026 05:00:00 AM | PET [GMT-05:00] | 90 | 5:00 | Yes | Site will isoloted due to Single point of failure |  | Yes |  |  |  | Completed
2026-02-09 | 39 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For A Mandatory Customer Troubleshooting. Your Circuit(S) Will Be Impacted During This Maintenance Window As Indicated Below. We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 12/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 |  | Traffic will failover to BVPN - Underlay PJVI029. a short blip for failover might experience | [5 empty] | Completed
2026-02-09 | 40 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For Routine Splicing. Your Circuit(S)May Experience Fluctuating Impact, If Down For More Than 10 Minutes Please Call Out Change Management Call Center.We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 13/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to BVPN - Underlay PJVI029. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-02 | 41 | IGO | PDEL2985 | Planned Outage Notifications , <P>Data Sa Pe For Dnos Upgradation Of Dl-Me01-Qcr04 At Delhi-Vsb</P> | Carrier Maintenace | GURUGRAM | INDIA | APAC | 14/FEB/2026 09:00:00 PM | IST [GMT+05:30] | 90 | 03:50 | No | Traffic will failover to PDEL2985. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-02 | 42 | DVP | PRKE082 | Scheduled Maintenance In Our Subcontractor'S Network | Carrier Maintenace | VALLENSBÆK STRAND | DENMARK | EUROPE | 16/FEB/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 30 | 05:99 | No | Traffic will failover to PRKE083. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-09 | 43 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For A Mandatory Customer Troubleshooting. Your Circuit(S) Will Be Impacted During This Maintenance Window As Indicated Below. We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 17/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to PJVI029. a short blip for failover might experience |  | Yes |  |  |  | Completed
2026-02-09 | 44 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For Routine Splicing. Although No Impact To Your Circuit(S) Listed Below Is Expected, This Maintenance Is Deemed Potentially Service Affecting. We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 19/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to PJVI029. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-09 | 45 | BUA | PQLV037 | Scheduled Maintenance Window To Enhance Network Performance And Reliability, Ensuring A Better Quality To Our Customers Maintenance Window To Improve Network | Carrier Maintenace | VICTORIA | ARGENTINA | LAM | 12/FEB/2026 02:00:00 AM | ART [GMT-03:00] | 60 | 01:00 | No | Traffic will failover to BVPN - Underlay PQLV036. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-30 | 46 | PAN | PPTY375 | Description Perform The Hip�Dromo 2 Segment Change, Eliminating Multiple Damaged Junction Boxes To Improve Network Performance. | Carrier Maintenace | PANAMA CITY | PANAMA | LAM | 12/FEB/2026 09:00:00 PM | GMT-05:00 | 90 | 08:00 | No | Traffic will failover to BVPN - Underlay PPTY376. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-30 | 47 | OKH | PHCC017 | Software Upgrades To Improve System Performance And Reliability. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 12/FEB/2026 12:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | No | Traffic will failover to PHCC016. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-02 | 48 | PLA | PLIM1002 | These Works Aim To Keep Our Networks In Optimal Condition. | Carrier Maintenace | SAN ISIDRO | PERU | LAM | 12/FEB/2026 05:00:00 AM | PET [GMT-05:00] | 90 | 05:00 | Yes | Site will isoloted due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-02-09 | 49 | OKH | PHCC017 | Software Upgrades To Improve System Performance And Reliability. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 12/FEB/2026 05:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | No | Traffic will failover to PHCC016. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-01-30 | 50 | OKH | PHCC017 | Software Upgrades To Improve System Performance And Reliability. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 13/FEB/2026 12:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | No | Traffic will failover to PHCC016. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-09 | 51 | PAN | PPTY375 | Description Perform The Hip�Dromo 2 Segment Change, Eliminating Multiple Damaged Junction Boxes To Improve Network Performance. | Carrier Maintenace | PANAMA CITY | PANAMA | LAM | 13/FEB/2026 02:00:00 AM | GMT-05:00 | 90 | 08:00 | No | Traffic will failover to BVPN - Underlay PPTY376. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-02 | 52 | PLA | PLIM1002 | These Works Aim To Keep Our Networks In Optimal Condition. | Carrier Maintenace | SAN ISIDRO | PERU | LAM | 13/FEB/2026 05:00:00 AM | PET [GMT-05:00] | 90 | 05:00 | Yes | Site will isoloted due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-02-04 | 53 | FRE | PFCH009 | We Will Be Performing Preventive Maintenance On Equipment To Ensure Proper Operation. | Carrier Maintenace | FRESNO | UNITED STATES | NAM | 17/FEB/2026 08:00:00 AM | PT [GMT-08:00 DST= GMT-07:00] | 5 | 06:00 | No | Traffic will failover to PFCH010. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-09 | 54 | BRA | PRIO1301 | 25747 - Reparo Definitivo De Cabo Com Corte Parcial | Carrier Maintenace | RIO DE JANEIRO | BRAZIL | LAM | 19/FEB/2026 11:00:00 AM | BR [GMT-03:00] | 200 | 04:00 | No | Traffic will failover to PRIO1300. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-09 | 55 | WNJ | PJVI028 | Crown Castle Fiber Will Be Conducting A Required Maintenance At The Above-Listed Location For Routine Splicing. Although No Impact To Your Circuit(S) Listed Below Is Expected, This Maintenance Is Deemed Potentially Service Affecting. We Apologize For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 20/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to PJVI029. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-11 | 56 | CUD | PSFZ30020 | Breakfix Maintenance : We Will Be Performing Corrective Maintenance On Equipment To Provide Improved Network Reliability. | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 19/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 60 | 06:00 | Yes | Site will isoloted due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-02-13 | 57 | CAP | PCPT665 | Network : OGN Region : IMEAR/South Africa Changes Category : xconnect rehome Changes Type : xconnect rehome Service Impact : no Change Window : WE Priority : 1 Duration : 2 hours Devices : BCPT5052/BCPT819 /BCPT9810 impacted services : BCPT5052/BCPT819 /BCPT9810 FE details:Justin Williams //justin.williams@altron.com Change Description : Hello team, As per trigger from NSP, existing teraco xconnect rehome inside the same cabinet (C_CH4_L03) into different device (from BCPT819 to BCPT9810) current topo: BCPT5052 -xe-1/1/0:0--------------<CPTCPT041, SO141881, 10G> ------------- Te1/2/0 - BCPT819 Target topo: BCPT5052 xe-1/1/0:0--------------<CPTCPT041, SO141881, 10G> ------------- Xe2/1/0-BCPT9810 <Build & Prov Owner> : KELLOUAI Yassir Requested date: FEB-21-2026, 18.00 to 20.00 GMT Thank you for your support. | Backbone Maintenace | CAPE TOWN | SOUTH AFRICA | EMEA | 21/FEB/2026 06:00:00 PM |  | 120 | 02:00 | No | Traffic will failover to PCPT666. a short blip for failover might experience | Yes | No | Yes |  |  | Completed
2026-02-11 | 58 | BRA | PRIO1301 | 25747 - Reparo Definitivo De Cabo Com Corte Parcial | Carrier Maintenace | RIO DE JANEIRO | BRAZIL | LAM | 25/FEB/2026 11:00:00 AM | EST [GMT-5:00] | 200 | 04:00 | No | Traffic will failover to the redundant router PRIO1300 | Yes | No | Yes |  |  | Cancelled
2026-02-11 | 59 | WEY | PLHR2486 | Scheduled Maintenance In Our Subcontractor'S Network | Carrier Maintenace | WEYBRIDGE | UNITED KINGDOM | EUROPE | 24/FEB/2026 12:05:00 AM | EST [GMT-5:00] | 210 | 05:91 | No | Traffic will failover to PLHR2485. a short blip for failover might experience | Yes | No | Yes |  |  | Completed
2026-02-13 | 60 | WNJ | PJVI028 | *** Rescheduled - Please Note New Date ***Please Note This Maintenance Has Been Rescheduled To The Dates/Times Listed Above. Crown Castle Fiber Apologizes For Any Resulting Inconvenience And Assure You Of Our Efforts To Minimize Any Service Disruption. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 26/FEB/2026 05:00:00 AM | EST [GMT-5:00] | 60 | 06:00 | No | Traffic will failover to PJVI029. a short blip for failover might experience | Yes | Yes | Yes |  |  | Completed
2026-02-18 | 61 | LCN | PLNK021 | OUR PROVIDER NEEDS TO PERFORM MAINTENANCE ON OUR MANAGED SERVICES PLATFORM RELATED TO SERVICE MIGRATION. | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 24/FEB/2026 07:00:00 AM | PT [GMT-08:00 DST= GMT-07:00] | 30 | 06:00 | NO | Traffic will failover to PLNK020. a short blip for failover might experience | Yes | No | Yes |  |  | Completed
2026-02-20 | 62 | ALC | PMAD6083 | SCHEDULED MAINTENANCE IN OUR SUBCONTRACTOR'S NETWORK | Carrier Maintenace | MADRID | SPAIN | EUROPE | 25/FEB/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 420 | 07:00 | NO | Traffic will failover to BVPN - Underlay PMAD6082. a short blip for failover might experience | Yes | No | Yes |  |  | Completed
2026-02-20 | 63 | IBV | PBLR1592 | RING SPLITTING ¦¦ CHN_PME_904_8AC_B_CNCS540R1 84 | Carrier Maintenace | BENGALURU | INDIA | APAC | 25/FEB/2026 06:30:00 PM | IST [GMT+05:30] | 360 | 06:00 | NO | Traffic will failover to BVPN - Underlay PBLR1593. a short blip for failover might experience | Yes | No | Yes |  |  | Completed
2026-02-23 | 64 | WNJ | PJVI028 | CROWN CASTLE FIBER WILL BE CONDUCTING A REQUIRED MAINTENANCE AT THE ABOVE-LISTED LOCATION FOR ROUTINE SPLICING. ALTHOUGH NO IMPACT TO YOUR CIRCUIT(S) LISTED BELOW IS EXPECTED, THIS MAINTENANCE IS DEEMED POTENTIALLY SERVICE AFFECTING. WE APOLOGIZE FOR ANY RESULTING INCONVENIENCE AND ASSURE YOU OF OUR EFFORTS TO MINIMIZE ANY SERVICE DISRUPTION. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 03/MAR/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to redundant router PJVI029 | Yes | Yes | Yes |  |  | Completed
2026-02-27 | 65 | NYN | PZRN066 | Emergency MAINTENANCE / WORKS YOUR BELOW MENTIONED SERVICE HAS TO BE INTERRUPTED.WE ARE ANXIOUS TO KEEP THE NECESSARY INTERRUPTION TIME AS SHORT AS POSSIBLE. | Carrier Maintenace | NYON | SWITZERLAND | EUROPE | 04/MAR/2026 12:00:00 AM | CET [GMT+01:00 DST= GMT+02:00] | 5 | 05:00 | No | As communicated by carrier, Service disruption is of approximately 5 minutes or less for the secondary WAN link connecting to router PZRN066. However, traffic will be failed over to redundant WAN link connecting to underlay primary router PZRN065 which makes no service disruption to the site. | Yes | Yes | Yes |  |  | Completed
2026-02-20 | 66 | BRA | PRIO1301 | UFINET WILL CARRY OUT EMERGENCY MAINTENANCE SERVICES AS NEEDED. DESPITE THE URGENT NATURE OF THESE ACTIVITIES, WE WILL MAKE EVERY EFFORT TO PROVIDE PRIOR NOTIFICATION WHENEVER POSSIBLE. BELOW, YOU WILL FIND FURTHER DETAILS REGARDING THE MAINTENANCE WINDOW | Carrier Maintenace | RIO DE JANEIRO | BRAZIL | LAM | 05/MAR/2026 09:00:00 AM | BR [GMT-03:00] | 240 | 04:00 | NO | Traffic will failover to redundant router PRIO1300 | Yes | Yes | Yes |  |  | Completed
2026-02-20 | 67 | CUD | PSFZ30020 | TO MAINTAIN NETWORK PERFORMANCE AND STABILITY WE WILL BE MIGRATING CIRCUITS TO AN OPTIMUM FIBER PATH. | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 06/MAR/2026 05:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-02-20 | 68 | CUD | PSFZ30020 | TO MAINTAIN NETWORK PERFORMANCE AND STABILITY WE WILL BE MIGRATING CIRCUITS TO AN OPTIMUM FIBER PATH. | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 06/MAR/2026 05:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-02-20 | 69 | OKH | PHCC017 | SOFTWARE UPGRADES IN KINGSTON, NY | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 05/MAR/2026 10:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | No | Yes |  |  | Completed
2026-02-20 | 70 | PAN | PPTY375 | ACTIVITY HAS BEEN RESCHEDULED PERFORM SEGMENT CHANGES IN THE CAMPO LINDBERGH SECTOR, ELIMINATING MULTIPLE DAMAGED JUNCTION BOXES TO IMPROVE NETWORK PERFORMANCE. | Carrier Maintenace | PANAMA CITY | PANAMA | LAM | 06/MAR/2026 02:00:00 AM | GMT-05:00 | 120 | 09:00 | NO | Traffic will failover to BVPN - Underlay PPTY376 | Yes | No | Yes |  |  | Completed
2026-02-20 | 71 | OKH | PHCC017 | SOFTWARE UPGRADES IN KINGSTON, NY | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 06/MAR/2026 10:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | No | Yes |  |  | Completed
2026-02-23 | 72 | WNJ | PJVI028 | *** RESCHEDULED - PLEASE NOTE NEW DATE ***PLEASE NOTE THIS MAINTENANCE HAS BEEN RESCHEDULED TO THE DATES/TIMES LISTED ABOVE. CROWN CASTLE FIBER APOLOGIZES FOR ANY RESULTING INCONVENIENCE AND ASSURE YOU OF OUR EFFORTS TO MINIMIZE ANY SERVICE DISRUPTION. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 06/MAR/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to redundant router PJVI029. | Yes | Yes | Yes |  |  | Completed
2026-02-25 | 73 | WNJ | PJVI028 | *** RESCHEDULED - PLEASE NOTE NEW DATE ***PLEASE NOTE THIS MAINTENANCE HAS BEEN RESCHEDULED TO THE DATES/TIMES LISTED ABOVE. CROWN CASTLE FIBER APOLOGIZES FOR ANY RESULTING INCONVENIENCE AND ASSURE YOU OF OUR EFFORTS TO MINIMIZE ANY SERVICE DISRUPTION. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 06/MAR/2026 05:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to redundant router PJVI029. | Yes | Yes | Yes |  |  | Rescheduled
2026-02-25 | 74 | SBM | PHLA020 |  METROFIBRE VENDOR TECHNICIANS WILL REHABILITATE FIBRES AT HAND HOLE GH000099 ROUTE, G01P09, G30P40, AND G20P35 TO AID IN SERVICE STABILITY AND EFFICIENCY. | Carrier Maintenace | SANDTON | SOUTH AFRICA | EMEA | 11/MAR/2026 10:00:00 PM | SAST [GMT+02:00] | 600 | 10:00 | No | Traffic will failover to redundant router PHLA021. | Yes | Yes | Yes |  |  | Completed
2026-02-25 | 75 | BRA | PRIO1301 | UFINET WILL CARRY OUT EMERGENCY MAINTENANCE SERVICES AS NEEDED. DESPITE THE URGENT NATURE OF THESE ACTIVITIES, WE WILL MAKE EVERY EFFORT TO PROVIDE PRIOR NOTIFICATION WHENEVER POSSIBLE. BELOW, YOU WILL FIND FURTHER DETAILS REGARDING THE MAINTENANCE WINDOW | Carrier Maintenace | RIO DE JANEIRO | BRAZIL | LAM | 11/MAR/2026 09:00:00 AM | BR [GMT-03:00] | 240 | 04:00 | No | Traffic will failover to redundant router PRIO1300. | Yes | Yes | Yes |  |  | Completed
2026-02-27 | 76 | PAN | PPTY376 | DESCRIPTION PREVENTIVELY UPGRADE THE OPERATING SYSTEM VERSION OF THE RCE PANAMA NCS FROM VERSION 7.4.2 TO VERSION 7.11.21 FOR BUG FIXES. NO. 11. | Carrier Maintenace | PANAMA CITY | PANAMA | LAM | 10/MAR/2026 05:00:00 AM | GMT-05:00 | 60 | 03:00 | No | Traffic will failover to BVPN - Underlay PPTY375. | Yes | No | Yes |  |  | Completed
2026-02-27 | 77 | PGG | PPSE022 | THE PURPOSE OF THIS ACTIVITY IS TO EXECUTE A SOFTWARE UPGRADE | Carrier Maintenace | GUAYAMA | PUERTO RICO | LAM | 10/MAR/2026 06:00:00 AM | AT [GMT-04:00] | 60 | 02:00 | No | Traffic will failover to redundant router PPSE021. | Yes | No | Yes |  |  | Completed
2026-02-27 | 78 | SJB | PSYQ032 | EQUIPMENT UPGRADE | Carrier Maintenace | CARTAGO | COSTA RICA | LAM | 11/MAR/2026 05:59:00 AM | HN [GMT-06:00] | 300 | 05:10 | No | Traffic will failover to redundant router PSYQ033. | Yes | Yes | Yes |  |  | Completed
2026-03-04 | 79 | PUL | PHLP033 | REENGINEERING FO PATH AT XCC KELAPA GADING | Carrier Maintenace | KECAMATAN CAKUNG | INDONESIA | APAC | 10/MAR/2026 01:00:00 PM | WIST [GMT+07:00] | 300 | 10:00 | No | Traffic will failover to BVPN - Underlay Router PHLP032. | Yes | No | Yes |  |  | Completed
2026-02-27 | 80 | BOW | PBOG1559 | DESCRIPTION MIGRACION CONTROLADA DE FUENTES PRINCIPAL Y BACK UP DEL EQUIPO HUAWEI F2A EN NODO WBP HACIA DOS NUEVOS RECTIFICADORES. | Carrier Maintenace | COTA | COLOMBIA | LAM | 13/MAR/2026 04:00:00 AM | GMT-05:00 | 10 | 05:00 | No | Traffic will failover to redundant router PBOG1560. | Yes | Yes | Yes |  |  | Completed
2026-03-02 | 81 | NAV | PUTC561 | SCHEDULED MAINTENANCE IN OUR SUBCONTRACTOR'S NETWORK | Carrier Maintenace | AMERSFOORT | NETHERLANDS | EUROPE | 16/MAR/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 360 | 06:00 | Minimal | The maintenance activity is scheduled from 11:00 PM to 5:00 AM GMT which falls under Out of business hour for the site, hence impact would be minimal. | Yes | Yes | Yes |  |  | Completed
2026-03-04 | 82 | CUD | PSFZ30020 | TO MAINTAIN NETWORK PERFORMANCE AND STABILITY WE WILL BE MIGRATING CIRCUITS TO AN OPTIMUM FIBER PATH. | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 13/MAR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-04 | 83 | OKH | PHCC017 | REASON: OUR PROVIDER WILL BE PERFORMING EQUIPMENT MAINTENANCE. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 16/MAR/2026 04:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | No | Traffic will fail over to the redundant WAN link connected to the underlay router PHCC016, ensuring no service disruption to the site. | Yes | Yes | Yes |  |  | Completed
2026-03-04 | 84 | OKH | PHCC017 | REASON: OUR PROVIDER WILL BE PERFORMING EQUIPMENT MAINTENANCE. | Carrier Maintenace | EAST DURHAM | UNITED STATES | NAM | 17/MAR/2026 04:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 0 | 06:00 | No | Traffic will fail over to the redundant WAN link connected to the underlay router PHCC016, ensuring no service disruption to the site. | Yes | Yes | Yes |  |  | Completed
2026-03-04 | 85 | WNJ | PJVI028 | *** RESCHEDULED - PLEASE NOTE NEW DATE ***PLEASE NOTE THIS MAINTENANCE HAS BEEN RESCHEDULED TO THE DATES/TIMES LISTED ABOVE. CROWN CASTLE FIBER APOLOGIZES FOR ANY RESULTING INCONVENIENCE AND ASSURE YOU OF OUR EFFORTS TO MINIMIZE ANY SERVICE DISRUPTION. | Carrier Maintenace | WARREN | UNITED STATES | NAM | 19/MAR/2026 04:00:00 AM | EST [GMT-5:00] | 60 | 06:00 | No | Traffic will failover to redundant router PJVI029. | Yes | Yes | Yes |  |  | Completed
2026-03-09 | 86 | LCN | PLNK021 | SCHEDULED MAINTENANCE IN OUR SUBCONTRACTOR'S NETWORK | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 18/MAR/2026 12:00:00 PM | CT [GMT-06:00 DST= GMT-05:00] | 90 | 04:00 | NO | Traffic will failover to redundant router PLNK020 | Yes | Yes | Yes |  |  | Completed
2026-03-17 | 87 | CUD | PSFZ30020 | BREAKFIX MAINTENANCE : WE WILL BE REPLACING EQUIPMENT TO CLEAR ALARMS AND PROVIDE IMPROVED NETWORK OPERATION. | Carrier Maintenace | LINCOLN | UNITED STATES | AMER | 19/MAR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-18 | 88 | UMN | PJDT020 | EMERGENCY MAINTENANCE : WE WILL BE PERFORMING SOFTWARE MAINTENANCE ON EQUIPMENT TO ENSURE NETWORK RELIABILITY. | Carrier Maintenace | MINNEAPOLIS | UNITED STATES | AMER | 19/MAR/2026 05:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 30 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed | Emergency
2026-03-09 | 89 | CUD | PSFZ30020 | SCHEDULED MAINTAINENCE | Carrier Maintenace | LINCOLN | UNITED STATES | NAM | 20/MAR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-12 | 90 | WAR | PWAW14406 | MODERNIZATION WORKS IN OPL INFRASTRUCTURE THERE MAY BE SOME SERVICE INTERRUPTION. | Carrier Maintenace | WARSZAWA | POLAND | EMEA | 24/MAR/2026 11:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 60 | 06:00 | NO | Traffic will failover to redundant router PWAW14407 | Yes | Yes | Yes |  |  | Completed
2026-03-20 | 91 | URS | PRIC197 | LUMEN&#65533;S 3RD PARTY PROVIDER WILL PERFORM MAINTENANCE WITHIN THEIR NETWORK. THIS HAS BEEN DESIGNATED AS ESSENTIAL. THE NATURE OF THIS WORK IS TO IMPLEMENT A FIBER REPAIR MAINTENANCE AND IS REQUIRED IN ORDER TO IMPROVE NETWORK RELIABILITY. | Carrier Maintenace | RICHMOND | UNITED STATES | AMER | 23/MAR/2026 05:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 1 | 05:00 | NO | Traffic will failover to redundant router PRIC198 | Yes | Yes | Yes |  |  | Completed
2026-03-20 | 92 | THX | PHSZ104 | URGENT CIRCUIT MAINTENANCE BY THE CIRCUIT PROVIDER | Carrier Maintenace | XINFENG TOWNSHIP | TAIWAN | APAC | 25/MAR/2026 01:30:00 AM | CST [GMT+08:00] | 60 | 03:50 | NO | Traffic will failover to redundant router PHSZ103 | Yes | Yes | Yes |  |  | Completed
2026-03-20 | 93 | IBV | PBLR1592 | RING SPLITTING ¦¦ CHN_PME_904_8AC_B_CNCS540R1 84 | Carrier Maintenace | BENGALURU | INDIA | APAC | 25/MAR/2026 06:30:00 PM | IST [GMT+05:30] | 360 | 06:00 | NO | Traffic will failover to redundant router PBLR1593 | Yes | Yes | Yes |  |  | Completed
2026-03-23 | 94 | UMN | PJDT020 | WE WILL BE PERFORMING SOFTWARE MAINTENANCE ON EQUIPMENT TO ENSURE NETWORK RELIABILITY. | Carrier Maintenace | MINNEAPOLIS | UNITED STATES | AMER | 26/MAR/2026 05:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 30 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-20 | 95 | CUD | PSFZ30020 | BREAKFIX MAINTENANCE : WE WILL BE PERFORMING PREVENTIVE MAINTENANCE ON EQUIPMENT TO ENSURE PROPER OPERATION. | Carrier Maintenace | LINCOLN | UNITED STATES | AMER | 31/MAR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 20 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-30 | 96 | CTS | PSHA3885 | URGENT CIRCUIT MAINTENANCE BY CIRCUIT PROVIDER | Carrier Maintenace | PUDONG | CHINA | APAC | 31/MAR/2026 02:00:00 PM | CST [GMT+08:00] | 60 | 06:00 | NO | Traffic will failover to redundant router PSHA3884 | Yes | Yes | Yes |  |  | Completed
2026-03-20 | 97 | CUD | PSFZ30020 | SCHEDULED MAINTAINENCE | Carrier Maintenace | LINCOLN | UNITED STATES | AMER | 03/APR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-25 | 98 | CUD | PSFZ30020 | BREAKFIX MAINTENANCE : WE WILL BE PERFORMING CORRECTIVE MAINTENANCE ON EQUIPMENT TO PROVIDE IMPROVED NETWORK RELIABILITY. | Carrier Maintenace | LINCOLN | UNITED STATES | AMER | 02/APR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 180 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-03-30 | 99 | BUA | PQLV037 | INSTALLATION OF NEW EQUIPMENT IN THE RACK | Carrier Maintenace | VICTORIA | ARGENTINA | AMER | 06/APR/2026 12:00:00 PM | ART [GMT-03:00] | 1 | 04:00 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-03-30 | 100 | BUA | PQLV037 | INSTALLATION OF NEW EQUIPMENT IN THE RACK | Carrier Maintenace | VICTORIA | ARGENTINA | AMER | 06/APR/2026 08:00:00 PM | ART [GMT-03:00] | 600 | 10:00 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-03-30 | 101 | BUA | PQLV037 | NEW CABLING AND RACK INSTALLATION | Carrier Maintenace | VICTORIA | ARGENTINA | AMER | 07/APR/2026 08:00:00 PM | ART [GMT-03:00] | 600 | 10:00 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-04-03 | 102 | IBV | PBLR1592 | AUDIT CORRECTION ¦¦ BGL_MSU_901_2NP_CASR9KTR138 | Carrier Maintenace | BENGALURU | INDIA | APAC | 07/APR/2026 06:30:00 PM | IST [GMT+05:30] | 120 | 06:00 | No | Traffic will failover to redundant router PBLR1593 | Yes | Yes | Yes |  |  | Completed
2026-04-06 | 103 | WNJ | PJVI028 | CROWN CASTLE FIBER WILL BE CONDUCTING A REQUIRED MAINTENANCE AT THE ABOVE-LISTED LOCATION FOR ROUTINE SPLICING. YOUR CIRCUIT(S) WILL BE IMPACTED DURING THIS MAINTENANCE WINDOW AS INDICATED BELOW. WE APOLOGIZE FOR ANY RESULTING INCONVENIENCE AND ASSURE YOU OF OUR EFFORTS TO MINIMIZE ANY SERVICE DISRUPTION. | Carrier Maintenace | WARREN | UNITED STATES | AMER | 11/APR/2026 04:00:00 AM | EST [GMT-5:00] | 360 | 06:00 | No | Traffic will failover to redundant router PJVI029. | Yes | Yes | Yes |  |  | Rescheduled
2026-03-30 | 104 | BUA | PQLV037 | HOT SWAP MIGRATION OF SERVICES FROM LEGACY INFRASTRUCTURE TO THE NEW PLATFORM | Carrier Maintenance | VICTORIA | ARGENTINA | AMER | 08/APR/2026 08:00:00 PM | ART [GMT-03:00] | 600 | 10:00 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-03-30 | 105 | BUA | PQLV037 | RACK CLEANUP AND FINAL ADJUSTMENTS | Carrier Maintenance | VICTORIA | ARGENTINA | AMER | 09/APR/2026 08:00:00 PM | ART [GMT-03:00] | 600 | 10:00 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-04-01 | 106 | CUD | PSFZ30020 | TO MAINTAIN NETWORK PERFORMANCE AND STABILITY WE WILL BE MIGRATING CIRCUITS TO AN OPTIMUM FIBER PATH. | Carrier Maintenance | LINCOLN | UNITED STATES | AMER | 09/APR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 60 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-04-03 | 107 | IBV | PBLR1592 | AUDIT CORRECTION ¦¦ BGL_MSU_901_1NP_CASR9KTR137 | Carrier Maintenance | BENGALURU | INDIA | APAC | 09/APR/2026 06:30:00 PM | IST [GMT+05:30] | 60 | 06:00 | No | Traffic will failover to redundant router PBLR1593 | Yes | Yes | Yes |  |  | Completed
2026-04-03 | 108 | ALC | PMAD6083 | SCHEDULED MAINTENANCE IN OUR SUBCONTRACTOR'S NETWORK | Carrier Maintenance | MADRID | SPAIN | EUROPE | 08/APR/2026 10:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 420 | 07:00 | No | Traffic will failover to redundant router PMAD6082 | Yes | Yes | Yes |  |  | Completed
2026-04-08 | 109 | CSB | PSZV606 | DETAILS URGENT NETWORK MAINTENANCE BY DYXNET | Carrier Maintenance | SUZHOU SHI | CHINA | APAC | 09/APR/2026 02:00:00 PM | CST [GMT+08:00] | 60 | 06:00 | No | Traffic from Underlay Router PSZV606 will failover to PSZV605 | Yes | Yes | Yes |  |  | Completed | Emergency
2026-04-08 | 110 | CSP | PSZV610 | DETAILS URGENT NETWORK MAINTENANCE BY DYXNET | Carrier Maintenance | SUZHOU | CHINA | APAC | 09/APR/2026 02:00:00 PM | CST [GMT+08:00] | 60 | 06:00 | No | Traffic from underlay router PSZV610 will failover to PSZV609 | Yes | Yes | Yes |  |  | Completed | Emergency
2026-04-01 | 111 | TAI | PTPE1934 | TFN NETWORK EQUIPMENT CARD MAINTENANCE. | Carrier Maintenance | ZHNOGZHENG DISTRICT | TAIWAN | APAC | 11/APR/2026 03:00:00 PM | GMT+08:00 | 1 | 07:00 | No | Traffic will failover to redundant router PTPE1935 | Yes | Yes | Yes |  |  | Completed
2026-04-01 | 112 | URS | PRIC197 | LUMEN INTENDS TO CARRY OUT INTERNAL MAINTENANCE WITHIN ITS NETWORK. THIS HAS BEEN DESIGNATED AS ESSENTIAL. THE NATURE OF THIS WORK IS TO PERFORM A CIRCUIT MIGRATION AND IS REQUIRED IN ORDER TO IMPROVE NETWORK RELIABILITY AND CONTINUE PROVIDING OPTIMAL SERVICE FOR OUR CLIENTS. AN ALTERNATE/BACKUP MAINTENANCE WINDOW HAS BEEN SCHEDULED IN THE EVENT WORK IS UNABLE TO BE COMPLETED ON THE PRIMARY NIGHT. CURRENTLY NO SERVICES ARE SCHEDULED TO BE IMPACTED ON THE ALTERNATE NIGHT. SHOULD THE ALTERNATE NIGHT BE DEEMED NECESSARY, YOU WILL RECEIVE AN UPDATED NOTIFICATION ADVISING WHICH SERVICES WILL BE IMPACTED ON THAT NIGHT. PLEASE SEE THE DATE AND TIMES OF THE ALTERNATE NIGHT BELOW. <B>LUMEN SINCERELY APOLOGIZES FOR ANY INCONVENIENCE CAUSED BY THIS MAINTENANCE</B>. , NA | Carrier Maintenance | RICHMOND | UNITED STATES | AMER | 14/APR/2026 04:00:00 AM | ET [GMT-05:00 DST= GMT-04:00] | 20 | 06:00 | No | Traffic will failover to redundant router PRIC198 | Yes | Yes | Yes |  |  | Completed
2026-04-03 | 113 | PUL | PHLP032 | UPGRADE OS DISTRIBUTION SWITCH AT POP LA TAMAN TEKNO | Carrier Maintenance | KECAMATAN CAKUNG | INDONESIA | APAC | 16/APR/2026 04:00:00 PM | WIST [GMT+07:00] | 30 | 03:00 | Yes | Maintenance one router at a time and by sequence | Yes | Yes | Yes |  |  | Completed
2026-04-03 | 114 | PUL | PHLP033 | UPGRADE OS DISTRIBUTION SWITCH AT POP LA TAMAN TEKNO | Carrier Maintenance | KECAMATAN CAKUNG | INDONESIA | APAC | 16/APR/2026 04:00:00 PM | WIST [GMT+07:00] | 30 | 03:00 | Yes | Maintenance one router at a time and by sequence | Yes | Yes | Yes |  |  | Completed
2026-04-08 | 115 | HCM | PSGN912 | CMC WILL PERFORM CABLE MAINTENANCE PLAN TO ENSURE AND IMPROVE THE QUALITY OF THE SERVICE. | Carrier Maintenance | HO CHI MINH | VIET NAM | APAC | 16/APR/2026 03:00:00 PM | VN [GMT+07:00] | 240 | 04:00 | No | Traffic from PSGN912 will failover to PSGN913 | Yes | Yes | Yes |  |  | Completed
2026-04-08 | 116 | WNJ | PJVI028 | *** RESCHEDULED - PLEASE NOTE NEW DATE ***PLEASE NOTE THIS MAINTENANCE HAS BEEN RESCHEDULED TO THE DATES/TIMES LISTED ABOVE. CROWN CASTLE FIBER APOLOGIZES FOR ANY RESULTING INCONVENIENCE AND ASSURE YOU OF OUR EFFORTS TO MINIMIZE ANY SERVICE DISRUPTION. | Carrier Maintenance | WARREN | UNITED STATES | AMER | 21/APR/2026 04:00:00 AM | EST [GMT-5:00] | 60 | 06:00 | No | Traffic will failover to redundant router PJVI029. | Yes | Yes | Yes |  |  | Completed | Rescheduled
2026-04-10 | 117 | JMS | PHDD011 | Changement avec impact service | Backbone Maintenance | JAMSHORO | PAKISTAN | APAC | 18/APR/2026 12:00:00 PM |  | 120 | 0:05 | Yes | As part of the planned migration involving Route Reflectors (RRs), the network will experience temporary routing convergence events. Specifically, BGP sessions will reset and LDP will reconverge due to route refresh. (during routing convergence).Customers should not experience a full outage because the involved device is not expected to be disconnected or restarted. | Yes | Yes | Yes |  |  | Completed
2026-04-10 | 118 | JMS | PHDD012 | Changement avec impact service | Backbone Maintenance | JAMSHORO | PAKISTAN | APAC | 18/APR/2026 12:00:00 PM |  | 120 | 0:05 | Yes | As part of the planned migration involving Route Reflectors (RRs), the network will experience temporary routing convergence events. Specifically, BGP sessions will reset and LDP will reconverge due to route refresh. (during routing convergence).Customers should not experience a full outage because the involved device is not expected to be disconnected or restarted. | Yes | Yes | Yes |  |  | Completed
2026-04-10 | 119 | PKH | PKHI576 | Changement avec impact service | Backbone Maintenance | KARACHI | PAKISTAN | APAC | 18/APR/2026 12:00:00 PM |  | 120 | 0:05 | Yes | As part of the planned migration involving Route Reflectors (RRs), the network will experience temporary routing convergence events. Specifically, BGP sessions will reset and LDP will reconverge due to route refresh. (during routing convergence).Customers should not experience a full outage because the involved device is not expected to be disconnected or restarted. | Yes | Yes | Yes |  |  | Completed
2026-04-10 | 120 | PKH | PKHI575 | Changement avec impact service | Backbone Maintenance | KARACHI | PAKISTAN | APAC | 18/APR/2026 12:00:00 PM |  | 120 | 0:05 | Yes | As part of the planned migration involving Route Reflectors (RRs), the network will experience temporary routing convergence events. Specifically, BGP sessions will reset and LDP will reconverge due to route refresh. (during routing convergence).Customers should not experience a full outage because the involved device is not expected to be disconnected or restarted. | Yes | Yes | Yes |  |  | Completed
2026-04-17 | 121 | PUL | PHLP032 | MIGRATION SERVICE AT NODE PULOGADUNG | Carrier Maintenance | KECAMATAN CAKUNG | INDONESIA | APAC | 17/APR/2026 03:00:00 PM | WIST [GMT+07:00] | 60 | 07:00 | No | Traffic will failover to redundant router PHLP033 | Yes | Yes | Yes |  |  | Completed | Emergency
2026-04-10 | 122 | PUL | PHLP032 | REENGINEERING ODC/SHELTER TRUNK NODE AT POP LA PULOGADUNG | Carrier Maintenance | KECAMATAN CAKUNG | INDONESIA | APAC | 23/APR/2026 01:00:00 PM | WIST [GMT+07:00] | 300 | 09:00 | No | Traffic will failover to redundant router PHLP033 | Yes | Yes | Yes |  |  | Completed
2026-04-15 | 123 | UMN | PJDT020 | SCHEDULED MAINTAINENCE | Carrier Maintenance | MINNEAPOLIS | UNITED STATES | AMER | 28/APR/2026 05:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 360 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-04-24 | 124 | UMN | PJDT020 | DEMAND MAINTENANCE : | Carrier Maintenance | MINNEAPOLIS | UNITED STATES | AMER | 28/APR/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 360 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-04-29 | 125 | BUA | PQLV037 | SCHEDULED MAINTENANCE WINDOW TO ENHANCE NETWORK PERFORMANCE AND RELIABILITY, ENSURING A BETTER QUALITY TO OUR CUSTOMERS A EMERGENCY MAINTENANCE WINDOW HAS BEEN SCHEDULED TO PERFORM IMPROVEMENTS ON THE NETWORK INFRASTRUCTURE. DURING THIS PERIOD, YOU MAY EXPERIENCE TEMPORARY INSTABILITY, INCLUDING PACKET LOSS OR HIGH LATENCY. | Carrier Maintenance | VICTORIA | ARGENTINA | AMER | 30/APR/2026 05:00:00 AM | ART [GMT-03:00] | 60 | 05:00 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed | Emergency
2026-04-27 | 126 | CAP | PCPT665 | SCOPE Redeployment of card 3D 4x 10GE XFP Hello team As per trigger from NSP The scope of this project is redeployment of card 3D 4x 10GE XFP destination for redeployed card site CPTT02 device name BCPT9810 device model MX480 device sn JN1261523AFB slot 2 subslot 1 details attached Network OGN Region IMEARSouth africa Changes Category hardware Updates Changes Type card insertion Service Impact no Change Window BD LTP Priority 1 Duration 2 hours Devices BCPT9810 impacted services BCPT9810 FE detailsJustin Williams 27690063460 justinwilliamsaltroncom Build Prov Owner NCG in attachment Requested date AVR152026 2100 to 2200 LOCAL time | Backbone Maintenance | CAPE TOWN | SOUTH AFRICA | EMEA | 30/APR/2026 08:00:00 PM | SAT (GMT+2) | 60 | 01:00 | No | Traffic will failover to redundant router PCPT666 | Yes | Yes | Yes |  |  | Completed
2026-04-22 | 127 | MMR | PAZP096 | FIRMWARE UPDATE FOR NETWORK STABILITY OPTIMIZATION. | Carrier Maintenance | CIUDAD DE MÉXICO | MEXICO | AMER | 02/MAY/2026 04:00:00 AM | [GMT-06:00 DST= GMT-05:00] | 60 | 03:00 | No | Traffic will failover to redundant router PAZP095 | Yes | Yes | Yes |  |  | Completed
2026-04-22 | 128 | NYN | PZRN066 | DUE TO PLANNED MAINTENANCE / WORKS YOUR BELOW MENTIONED SERVICE HAS TO BE INTERRUPTED.WE ARE ANXIOUS TO KEEP THE NECESSARY INTERRUPTION TIME AS SHORT AS POSSIBLE. | Carrier Maintenance | NYON | SWITZERLAND | EUR | 05/MAY/2026 08:00:00 PM | CET [GMT+01:00 DST= GMT+02:00] | 30 | 03:00 | No | Traffic will be failed over to redundant WAN link connecting to underlay primary router PZRN065 which makes no service disruption to the site. | Yes | Yes | Yes |  |  | Completed
2026-04-22 | 129 | CQM | PYCV007 | ROGERS BUSINESS WILL UPGRADE 7210 CPE AND MEDIA CONVERTER DEVICES TO AN UPDATED VERSION OF TIMOS (DEVICE OPERATING SYSTEM) TO ENSURE CONTINUED RELIABILITY, STABILITY, AND FUNCTIONALITY. ROGERS BUSINESS METTRA À NIVEAU LES APPAREILS CPE 7210 ET LES CONVERTISSEURS DE MÉDIAS VERS UNE VERSION MISE À JOUR DE TIMOS (SYSTÈME D'EXPLOITATION DE L'APPAREIL) AFIN D'ASSURER LA CONTINUITÉ DE LEUR FIABILITÉ, DE LEUR STABILITÉ ET DE LEUR FONCTIONNALITÉ. | Carrier Maintenance | MONTRÉAL | CANADA | AMER | 06/MAY/2026 04:00:00 AM | EST [GMT-05:00 DST= GMT-04:00] | 30 | 06:00 | No | Traffic will failover to redundant router PYCV006 | Yes | Yes | Yes |  |  | Completed
2026-04-29 | 130 | CUD | PSFZ30020 | WE WILL BE PERFORMING PREVENTIVE MAINTENANCE ON EQUIPMENT TO ENSURE PROPER OPERATION. | Carrier Maintenance | LINCOLN | UNITED STATES | AMER | 05/MAY/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 180 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-04-29 | 131 | CUD | PSFZ30020 | WE WILL BE PERFORMING PREVENTIVE MAINTENANCE ON EQUIPMENT TO ENSURE PROPER OPERATION. | Carrier Maintenance | LINCOLN | UNITED STATES | AMER | 06/MAY/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 180 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-04-29 | 132 | CUD | PSFZ30020 | WE WILL BE PERFORMING PREVENTIVE MAINTENANCE ON EQUIPMENT TO ENSURE PROPER OPERATION. | Carrier Maintenance | LINCOLN | UNITED STATES | AMER | 07/MAY/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 180 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed
2026-04-30 | 133 | BUA | PQLV037 | SCHEDULED MAINTENANCE WINDOW TO ENHANCE NETWORK PERFORMANCE AND RELIABILITY, ENSURING A BETTER QUALITY TO OUR CUSTOMERS CHANGE CONFIGURATION FOR IMPROVE THE NETWORK | Carrier Maintenance | VICTORIA | ARGENTINA | AMER | 05/MAY/2026 07:15:00 AM | ART [GMT-03:00] | 45 | 02:25 | No | Traffic will failover to BVPN - Underlay PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-05-04 | 134 | UMN | PJDT020 | DEMAND MAINTENANCE : | Carrier Maintenance | MINNEAPOLIS | UNITED STATES | AMER | 05/MAY/2026 04:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 360 | 06:00 | Yes | Site will be isolated due to Single point of failure | Yes | Yes | Yes |  |  | Completed | Emergency
2026-04-29 | 135 | CAP | PCPT666 | TO UPGRADE THE ASR920 DEVICE FROM IOS VERSION FROM 6.6.3 TO 7.11.2. THIS IS REQUIRED TO ADDRESS BUGS AND VULNERABILITIES. | Carrier Maintenance | CAPE TOWN | SOUTH AFRICA | EMEA | 11/MAY/2026 09:59:00 PM | SAST [GMT+02:00] | 180 | 06:01 | No | Traffic will failover to PCPT665 | Yes | Yes | Yes |  |  | Completed
2026-05-04 | 136 | NYN | PZRN065 | DUE TO PLANNED MAINTENANCE / WORKS YOUR BELOW MENTIONED SERVICE HAS TO BE INTERRUPTED.WE ARE ANXIOUS TO KEEP THE NECESSARY INTERRUPTION TIME AS SHORT AS POSSIBLE. | Carrier Maintenance | NYON | SWITZERLAND | EUR | 18/MAY/2026 08:00:00 PM | CET [GMT+01:00 DST= GMT+02:00] | 10 | 03:00 | No | Traffic will failover to PZRN066. | Yes | Yes | Yes |  |  | Completed
2026-05-08 | 137 | IBV | PBLR1592 | IOS UPGRADE ¦¦ BGLLSUMPLLTEPERTR43186 | Carrier Maintenance | BENGALURU | INDIA | APAC | 18/MAY/2026 06:30:00 PM | IST [GMT+05:30] | 120 | 06:00 | No | As communicated by carrier, there would be no service disruption as traffic will be catered by WAN link connecting to redundant router PBLR1593 | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 138 | IBV | PBLR1592 | IOS UPGRADE ¦¦ BGLLSUMPLLTEPERTR43187 | Carrier Maintenance | BENGALURU | INDIA | APAC | 19/MAY/2026 06:30:00 PM | IST [GMT+05:30] | 180 | 06:00 | No | As communicated by carrier, there would be no service disruption as traffic will be catered by WAN link connecting to redundant router PBLR1593 | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 139 | DUN | PWAT031 | WE REQUIRE THIS MAINTENANCE WINDOW TO CUT IN NEW 100G NODES IN LONDON LD8 AND LONDON TELEHOUSE NORTH INTO THE RING. PLANNED WORKS DATE & TIME: START DATE/TIME: 2026-05-21 00:15:00 END DATE/TIME: 2026-05-21 06:00:00 MAINTENANCE WINDOW DURATION: 5 HOURS 45 MINUTES TIME ZONE: IST ( IRISH STANDARD TIME ) THE BELOW SERVICE(S) LISTED IN OUTAGE WILL EXPERIENCE SIXTY MINUTES OUTAGE (60MINS) DURING THE WORKS WINDOW. OUTAGE: NONE | Carrier Maintenance | DUNGARVAN | IRELAND | EUR | 20/MAY/2026 11:15:00 PM | WET [GMT DST= GMT+01:00 ] | 300 | 05:75 | No | As communicated by carrier, there would be no service disruption as traffic will be catered by WAN link connecting to redundant router PWAT034. | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 140 | JMS | PHDD009 | THIS IS TO INFORM YOU THAT PDL HAS PLANNED A POWER RELATED MAINTENANCE ACTIVITY AT MRD POP | Carrier Maintenance | JAMSHORO | PAKISTAN | IMEAR | 15/MAY/2026 09:00:00 PM | PKT [GMT+05:00] | 1 | 03:00 | No | Traffic will failover to redundant router PHDD010 | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 141 | PKH | PKHI30624 | THIS IS TO INFORM YOU THAT PDL HAS PLANNED A POWER RELATED MAINTENANCE ACTIVITY AT MRD POP | Carrier Maintenance | KARACHI | PAKISTAN | IMEAR | 15/MAY/2026 09:00:00 PM | PKT [GMT+05:00] | 1 | 03:00 | No | Traffic will failover to redundant router PKHI30625 | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 142 | PKH | PKHI575 | THIS IS TO INFORM YOU THAT PDL HAS PLANNED A POWER RELATED MAINTENANCE ACTIVITY AT MRD POP | Carrier Maintenance | KARACHI | PAKISTAN | IMEAR | 15/MAY/2026 09:00:00 PM | PKT [GMT+05:00] | 1 | 03:00 | No | Traffic will failover to redundant router PKHI576 | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 143 | BUA | PQLV037 | SCHEDULED MAINTENANCE WINDOW TO ENHANCE NETWORK PERFORMANCE AND RELIABILITY, ENSURING A BETTER QUALITY TO OUR CUSTOMERS. CHANGE CONFIGURATION FOR IMPROVE THE NETWORK | Carrier Maintenance | VICTORIA | ARGENTINA | AMER | 21/MAY/2026 07:15:00 AM | ART [GMT-03:00] | 180 | 03:73 | No | Traffic will failover to redundant router PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-05-15 | 144 | MMR | PAZP095 | THE FIRST SERVICE MIGRATION IS BEING CARRIED OUT AT THE SAN JERÓNIMO SITE. THE MIGRATION OF LOCAL INTERCONNECTIONS (EQUIPMENT TO EQUIPMENT) IS BEING PERFORMED. THIS SERVICE MIGRATION IS NECESSARY BECAUSE THE CURRENT RACK WILL BE REMOVED. | Carrier Maintenance | CIUDAD DE MÉXICO | MEXICO | AMER | 21/MAY/2026 05:00:00 AM | CST [GMT-6:00] | 360 | 06:00 | No | Traffic will failover to redundant router PAZP096 | Yes | Yes | Yes |  |  | Completed
2026-05-19 | 145 | PZN | PPOZ9280 | MODERNIZATION WORKS IN OPL INFRASTRUCTURE THERE MAY BE SOME SERVICE INTERRUPTION. | Carrier Maintenance | POZNAŃ | POLAND | EUR | 26/MAY/2026 10:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 15 | 07:50 | No | There would be no service disruption as traffic will be catered by WAN link connecting to redundant router PPOZ9279. | Yes | Yes | Yes |  |  | Completed
2026-05-13 | 146 | PGG | PPSE022 | THE PURPOSE OF THIS ACTIVITY IS TO MIGRATE THE SERVICES TO A NEW AND IMPROVED PLATFORM. | Carrier Maintenance | GUAYAMA | PUERTO RICO | AMER | 27/MAY/2026 03:30:00 AM | AT [GMT-04:00] | 360 | 06:00 | No | Traffic will failover to redundant router PPSE021 | Yes | Yes | Yes |  |  | Completed
2026-05-22 | 147 | DUG | PWAT034 | WE REQUIRE THIS MAINTENANCE WINDOW TO PROACTIVELY REPLACE FAULTY NETWORK CARDS IDENTIFIED BY THE VENDOR AS HAVING AN ELEVATED RISK OF FAILURE. PLANNED WORKS DATE & TIME: START DATE/TIME: 2026-05-29 01:00:00 END DATE/TIME: 2026-05-29 06:00:00 MAINTENANCE WINDOW DURATION: 5 HOURS TIME ZONE: IST ( IRISH STANDARD TIME ) THE BELOW SERVICE(S) LISTED IN OUTAGE OPERATING AT 10G AND 100G MAY EXPERIENCE UP TO A THIRTY MINUTE (30MINS) OUTAGE DURING THE MAINTENANCE WINDOW. OUTAGE: NONE | Carrier Maintenance | DUNGARVAN | IRELAND | EUR | 29/MAY/2026 12:00:00 AM | WET [GMT DST= GMT+01:00 ] | 300 | 05:00 | No | As communicated by carrier, there would be no service disruption as traffic will be catered by WAN link connecting to redundant router PWAT031. | Yes | Yes | Yes |  |  | Completed
2026-05-22 | 148 | LEV | PSLD026 | HEREBY WE INFORM YOU THAT SWAN IS GOING TO DO AN PLANNED MAINTENANCE WORK, WHICH WILL AFFECT YOUR SERVICE. | Carrier Maintenance | LEVICE | SLOVAKIA | EUR | 01/JUN/2026 09:30:00 PM | CET [GMT+01:00 DST= GMT+02:00] | 30 | 03:50 | No | There would be no service disruption due to this maintenance activity | Yes | Yes | Yes |  |  | Completed
2026-05-25 | 149 | RKA | PZLM184 | COLT WILL BE CONDUCTING A MAINTENANCE FOR NETWORK DESIGN REQUIREMENT ON OUR ACCESS ROUTER SAR4.ZRH IN ZURICH. THE MAINTENANCE SHOULD NOT RESULT IN ANY OUTAGE TO SERVICES, BUT PACKET LOSS MAY BE OBSERVED FOR A SHORT PERIOD DURING THE MAINTENANCE WINDOW. DURING THE WORKS A NEW CONFIGURATION WILL BE DEPLOYED ON THE DEVICE BY COLT 3RD LEVEL SUPPORT. AS MENTIONED, THERE IS NO DOWNTIME AS SUCH. THERE IS EVENTUALLY SOME PACKET LOSS DURING ROUTE CONVERGENCE. THE POTENTIAL PACKET LOSS IS IN A RANGE OF 0 TO 30 PACKETS. . THE MAINTENANCE SHOULD BE COMPLETED WITHIN THE 60 MINUTES OF THE ACTIVITY, BUT AN 2 HOUR WINDOW HAS BEEN QUOTED TO COVER ALL EVENTUALITIES. BACK-OUT PLAN 60 MINUTES ARE RESERVED TO REVERT BACK ANY CHANGES MADE, SHOULD OUR ENGINEERS EXPERIENCE ANY UNFORESEEN ISSUES . THE MENTIONED OUTAGE DURATION IS A BEST ESTIMATION FOR THE WORK AT HAND, BUT SHOULD YOU ASCERTAIN THAT YOU ARE EXPERIENCING ANY PROLONGED CONNECTION ISSUES EXCEEDING THIS DURING THE WORKS, PLEASE CONTACT OUR TECH | Carrier Maintenance | ROTKREUZ ZG | SWITZERLAND | EUR | 03/JUN/2026 08:00:00 PM | CET [GMT+01:00 DST= GMT+02:00] | 60 | 02:00 | No | As communicated by carrier, there would be no service disruption due to this maintenance activity. | Yes | Yes | Yes |  |  | Completed
2026-05-25 | 150 | CBT | PBOG1580 | UPDATE ROUTING ENGINE MASTER/BACKUP ON PSR JUNIPER MX960 TO HAVE THE LATEST APPROVED VERSION. | Carrier Maintenance | BOGOTA | COLOMBIA | AMER | 04/JUN/2026 05:00:00 AM | GMT-05:00 | 90 | 02:50 | No | Traffic will failover to redundant router PBOG1579 | Yes | Yes | Yes |  |  | Completed
2026-05-26 | 151 | IDP | PSLV005 | IOS UPGRADATION AT SIMMPLLTEPERTR134 | Carrier Maintenance | BADDI | INDIA | APAC | 04/JUN/2026 06:30:00 PM | IST [GMT+05:30] | 300 | 06:00 | No | As communicated by carrier, there would be no service disruption due to this activity | Yes | Yes | Yes |  |  | Completed
2026-06-01 | 152 | LEN | PLNK021 | MAINTENANCE ON IP PLATFORM RELATED TO JUNOS UPGRADE. | Carrier Maintenance | LINCOLN | UNITED STATES | AMER | 09/JUN/2026 09:00:00 AM | CT [GMT-06:00 DST= GMT-05:00] | 90 | 04:00 | No | Traffic will failover to redundant router PLNK020 | Yes | Yes | Yes |  |  | Completed
2026-06-08 | 153 | WNJ | PJVI029 | Prod avec Impact + CAB | Backbone Maintenance | WARREN | UNITED STATES | NAM | 14/JUN/2026 08:00:00 AM |  | 60 | 01:00 | No | The traffic will be failed over to redundant WAN link connecting to underlay router PJVI028 which makes no service disruption to the site. | Yes | Yes | Yes |  |  | Completed
2026-06-08 | 154 | OKH | PHCC017 | Prod avec Impact + CAB | Backbone Maintenance | EAST DURHAM | UNITED STATES | NAM | 14/JUN/2026 08:00:00 AM |  | 60 | 01:00 | No | Traffic will failover to redundant router PHCC016 | Yes | Yes | Yes |  |  | Completed
2026-06-10 | 155 | MNH | PMUC2640 | MAINTENANCE BY THE LOCAL CARRIER | Carrier Maintenance | MÜNCHEN | GERMANY | EUR | 17/JUN/2026 10:00:00 PM | CET [GMT+01:00 DST= GMT+02:00 ] | 30 | 06:00 | NO | There is no service impact as traffic will be failed over to link connecting to redundant SDWAN router PZMU060. | Yes | Yes | Yes |  |  | Completed
2026-06-10 | 156 | IBV | PBLR1592 | IOS UPGRADE ¦¦ BGLLSUMPLLTEPERTR43186 | Carrier Maintenance | BENGALURU | INDIA | APAC | 18/JUN/2026 06:30:00 PM | IST [GMT+05:30] | 120 | 06:00 | NO | As communicated by carrier, there would be no service disruption as traffic will be catered by WAN link connecting to redundant router PBLR1593. | Yes | Yes | Yes |  |  | Completed
2026-06-10 | 157 | IBV | PBLR1592 | IOS UPGRADE ¦¦ BGLLSUMPLLTEPERTR43187 | Carrier Maintenance | BENGALURU | INDIA | APAC | 19/JUN/2026 06:30:00 PM | IST [GMT+05:30] | 180 | 06:00 | NO | As communicated by carrier, there would be no service disruption as traffic will be catered by WAN link connecting to redundant router PBLR1593. | Yes | Yes | Yes |  |  | Completed
2026-06-22 | 158 | BUA | PQLV037 | SCHEDULED MAINTENANCE WINDOW TO ENHANCE NETWORK PERFORMANCE AND RELIABILITY, ENSURING A BETTER QUALITY TO OUR CUSTOMERS CHANGE CONFIGURATION FOR IMPROVE THE NETWORK | Carrier Maintenance | VICTORIA | ARGENTINA | AMER | 30/JUN/2026 10:00:00 AM | ART [GMT-03:00] | 60 | 02:00 | No | Traffic will failover to redundant router PQLV036. | Yes | Yes | Yes |  |  | Completed
2026-06-22 | 159 | CMI | PYYZ1421 | ROGERS BUSINESS WILL UPGRADE 7210 CPE AND MEDIA CONVERTER DEVICES TO AN UPDATED VERSION OF TIMOS (DEVICE OPERATING SYSTEM) TO ENSURE CONTINUED RELIABILITY, STABILITY, AND FUNCTIONALITY. | Carrier Maintenance | MISSISSAUGA | CANADA | AMER | 06/JUL/2026 04:00:00 AM | EST [GMT-05:00 DST= GMT-04:00] | 30 | 06:00 | No | Traffic will failover to redundant router | Yes | Yes | Yes |  |  | Completed
Note on O69: RAJAWAT Vishal OBS/OBI: there is only one critical component, if it fails, the entire site will lose connection and become isolated.
Note on D87: RAJAWAT Vishal OBS/OBI: Earlier this activity was planned on 6th March.